My understanding of the document “sop”:

1 Terminologies

Project center:
Project center cases:
  1) data patching
  2) data extraction
  3) inquiry / bug validation
  4) logging of the above cases
Master resource plan:
MasterDeployment excel:
Production server:
Staging environment:
PM Team:

2 Roles involved
1) developers
2) senior developers
3) pm / pe
4) clients
5) Shirley and Ronnie

3 Activities in daily work:
2.1 Developing(coding)
2.2 Testing and update to svn
2.3 Deploy bug fixes or enhancements
2.4 Process client requirements

Contents
1.0 Testing and deployment procedures
  1.1 Testing procedure diagram – for support cases
  1.2 Deployment procedure diagram – lead time for deployment is 1 day for planned cases to prepare for necessary document and database scripts
2.0 Production access procedures
  2.1 project center cases
  2.2 production access diagram
3.0 Creating a local copy of project database
  3.1 procedure diagram
4.0 Preventive measures and procedures regarding email functions

1.0 Testing and deployment procedures

Developers do Unit Test → Prepare screen shot and source compare →
PM / PE do do SIT at Staging Environment → Prepare screen shot and source compare →
User test and acceptance confirmation → all issues deployed to staging environment →
Deployment will only be done on Tuesday and Thursday →
Developers prepare the deployment plan(db changes, codes to deploy, data patching, web.config changes, sp changes, new sp, new tables) at least 3 hours before deployment →
Senior developer verify the deployment schedule →
Developers deploy following the verified schedule →
PM / PE update MasterDeployment excel for features and functionalities to deploy →
Prepare all the above documents before deployment →
Approve deviation from Ronnie or Shirley